## K-C Road
S. N. | Landslide |  |  | Location |  |  |  | Consult With | Slide Description | Structure | Private land | Environmental Mitigation Measues | Photo
| Chainage | Types of failure | Proposed Engineering Mitigation Measures | District | MP/RMP | Ward | Village
1 | 13350 | Cut slope failure and sliding in spoil at valley side | Bio-engineering Mitigation | Baitadi | Surnaye RMP | 6 | Raute | Mr. Gagan Singh Bist | Near Settlement, Hill Side: Vegetation (Bushes); Valley Side: Cultivable Land |  | Private Land( Dan Bdr Bista)
2 | 41900 | Debris deposited from cut slope | Plum Concrete Retaining wall (L=10m, H=2m) & Bio-engineering | Bajhang | Bidhadchir RMP | 4 | Melta | Mr. Sundar Singh | Barren land, Used for stone quarry by local, soil and rock flow by rian water each year |  | Private LandRaivaan Bohara and sundarsingh Nagari)
3 | 42075 | Debris deposited at road and drain & Debris from gully | Gabion Retaining Wall (L=5m,H=4m ) and Bio-engineering | Bajhang | Bidhadchir RMP | 4 | Tolyan | Mr. Man Bahadur Bohara | Near settlement, Barren land |  | Private Land(Damba kami)
4 | 58300 |  | Plum Concrete Wall (L=20m,H=5m), debris , drain, | Bajhang | Bidhadchir RMP | 8 | Dharan | Mr. Madan Adhakari | Vegetation (Bushes), debris flow , The land is being used fro stone quarry by the land owner and the stone pieces and dust s from quarry site flow over road | PC Culvert, Side drain | Private Land(Dhan Bdr Malla)
5 | 61630 | Wall failure at valley side, irrigation channel affected | Plum Concrete Wall (L=5m,H=3m) | Bajhang | Kedarshu RMP | 2 | Kedarshu | Mr. Ram Bahadur Rawal | Being Maintened by DRO Baitadi |  | Private Land
6 | 68100 | Cossing Requiued | Gabion Retaining Wall (L=12m , H=5) | Bajhang | Kedarshu RMP | 1 | Chaudaam |  | Near settlement, Water flow over road due to lack of cross drainage |  | Private (Purna Bhandari)
7 | 68200 | Cossing Requiued | Gabion Breast Wall (L=15,H=2), Drain & Bio-engineering | Bajhang | Kedarshu RMP | 1 | Chaudaam |  |  |  | Private-Bhalam Khola Bridge area
8 | 78700 | Existing Irrigation crossing damaged | 30m road settle vertically 2m, Retaining and Breast Structures with slightly shifting the alignment, Side Drain. (Detailed qunatity included in pavement design part) | Bajhang | R/S Durgathali RPM L/S Kedarshu | R/S 2 L/S 1 | Shudi Khola |  | Boarder of two Rural Municipality, Water Cource, Cultivable land both side, water being used for irrigation |  | Private(Laxmi raj kharel,Mairaj Giri and Shivaraj Joshi
9 | 82+500 | Cossing Requiued | Gabion Chcek Dams, Apron and Guide wall at US and DS Causeway=10m and Stone Pitching | Bajhang | Durgathali RPM | 2 | Mauri Bagar (Saanigad Khola) | Mr. Gagan Rawal | Near settlement, Existing water , water being used for water mill operation | Water mill (D/S side) | Private land (Cultivable land) D/S
10 | 82800 | Cossing Requiued |  | Bajhang | Durgathali RPM | 2 | Mauri Bagar |  | Near settlement, Existing water , water being used for water mill operation
11 | 97120 | Debris deposited at road and drain | Gabion Breast wall=175*3, Gabion Retaining =90*3, Drain=175m, Bio-engineering and debris clearance | Bajhang | Jayeprithvi MP | 7 | Subeda |  | No settlement, Irrigation canal valley side, | Irrigation canal | Private land(PramerajJoshi,Bishnubhakta joshi)
12 | 97550 | Cut slope failure | Gabion Breast wall=15*3, Drain=105m, Bio-engineering and debris clearance | Bajhang | Jayeprithvi MP | 7 | Subeda |  | Hill side: Private land, Settlement area, water flow duirng monsoon, structure settled |  | Private(Purendra Bdr Bam,Sher Bdr Bam,Prem Bdr Bam
13 | 98650 |  | Gabion breast wall=30m * 3m, Bio-engineering and Debris clearance | Bajhang | Jayeprithvi MP | 7 | Subeda |  | Baran land, Bushes area, Cut slope failure, near water source and water mill operated during monsoon | Gabion wall, water mill(operate during monsoon) | Private land(Paramraaj Upadhaya)
14 | 99320 | Huge debris flow in gullley. On 30th Jestha, a jeep was washed away. | Gabion breast wall =35m * 3m, Drain=15m, Landslide Clearance | Bajhang | Jayeprithvi MP | 7 | Koirali Khet |  | Natural water cource, debris flow over road | Caseway | Private(Paramraaj Upadhaya)
15 | 99500 | Valley side slide, tension crack along edge of pavement | Gabion breast wall=40*3, Retaining wall=18*3, drain=75m, Bio-engineering, debris clearance | Bajhang | Jayeprithvi MP | 6 | Koirali Khet |  | Neas Settlement, private land hill side, valley side bushes, road edge cracks | Gabion wall | Private(Ramlal Damai)
16 | 99900 | Causeway damaged | Gabion breast wall=13.5*3, drain=75m, Bio-engineering, debris clearance | Bajhang | Jayeprithvi MP | 6 | GodeliKhet Bazzar |  | Near water course, barren land, debris flow form hill | Causeway, gabion wall | Privateland
17 | 101000 |  | Gabion Breast Wall=20*3m, Causeway=15m, Apron, Guide wall, Drain, Debris clearance and Bio-engineering | Bajhang | Jayeprithvi MP | 8 | Chainpur |  | Small slide, toe cut failure, gabion wall damaged, | Gabion wall, | private land
18 | 104500 | Toe cutting, retaining wall collapse, road back cut, road closed for 3 days in Jestha, cross drain missing | Gabion breast wall=5*3, Bio-engineering and Debris clearance | Bajhang | Jayeprithvi MP | 9 | Chainpur |  | Near settlemetn (Chainpure), nare road junction (recently constructed), road edge damaged | Gabion wall | Private land(Jangabir Mijari)

## C-J Road
S. N. | Landslide |  |  |  | Location |  |  |  | Consult With | Slide Description | Impacts |  |  |  |  | Environmental Mitigation Measues | Photo
| Chainage | Severity | Types of failure | Proposed Engineering Mitigation Measures | District | MP/RMP | Ward | Village |  |  | Structure | Community Forest | Vegetation | Public Utilities | Private land
1 | 23+660 | Type 3 | Suface Scraping & Shallow Failue | Drain cum wall (2 locations), L=25m, H=1.5m, L=20m, H=1.0m, Repair of GW retaining wall at valley side, Jute netting and Bio-engineeing | Surkhet | Gurwakot | 9 | Vulke |  | Surface water problems, Bushes on valley side, Bheri River valley side, sone quarry by local | Gabion retaining wall |  |  | Drinking water pipeline
2 | 27+880 | Type 3 | Alluvium Deposit | Plum cascade (v-channel) on hillside, L=25m, Bio-engineering (Fascine & Palaside) | Surkhet | Gurwakot | 3 | Kurulle |  | Forest (Government Land), Electric pole at the top of slide | Road side drain |  |  | Electric pole, 1" HDEP water pipe
3 | 29+266 | Type 3 | Debris Flow | Gabion Breast wall, L=10m, H=3m Repair existing pipe culvert (divert water flow to culvert on U/S), Raise the GW breast wall, L=20m, H=1m, Check dam (3 location), L=15m, H=3m, Jut netting, Stone rip rap | Surkhet | Gurwakot | 3 | Kurulle |  | Natural water channel, cross drain chocked, | Pipe culverd, drainage (damaged) |  |  | 1" HDEP water pipe
4 | 29+986 | Type 2 | Gully erosion | GW cascade at hillside, L= 40m (Existing GW breast wall-good condition) | Surkhet | Gurwakot | 3 | Kurulle |  | Forest area, Bheri river (valley side), Gabion wall constructed by DRO and in good condition | Gabion breast wall |  | Sallo | 2" HPEP water pipe (Slope top)

## S-M Road
S. N. | Landslide |  |  |  | Location |  |  |  | Consult With | Slide Description | Impacts |  | Environmental Mitigation Measues | Photo
| Chainage | Severity | Types of failure | Proposed Engineering Mitigation Measures | District | MP/RMP | Ward | Village |  |  | Structure | Private land
1 | 98550 | Type 3 | Debris fall with big Stone | Drain cum wall, L=10m, H=1.5m, Boulder Removal (4m*3m*2m) | Salyan | Bagchaur MP | 4 | Dharmasala |  | Huge boulder along with debris, near settlement area |  | Private land
2 | 105430 | Type 2 | Alluvium deposit (Quarry site) | Drain cum Plum breast wall, L=55m, H=2m, PC head wall, L=5m, H=1.5m (raised), Pavement Rehab, L=55m, Bio-engineering (L=55m, H=10m) | Salyan | Bagchaur MP | 4 | Nigal Pani |  | Near settlement area, private land, stone quarry site |  | Private land
3 | 106400 | Type 2 | Gabion Collapse (Road edge) | GW retaining wall, L=25m, H=4m (dismantle existing GW wall), Debris clearance, L=20m, H=10m) at 100m towards musikot | South Rukum | Tribini RMP | 6 | Khaila |  | Aailani land (Forest area), near settlement | Gabion retaining wall | Private land
4 | 107000 | Type 3 | Road Edge damaged | Plum retaining wall, L=25m, H=4m (houses at downside) | South Rukum | Tribini RMP | 6 | Ranchipu |  | Settlement area, 2 house below slide, retaining wall collaps |  | Private land
5 | 107+770 | Type 1 | Deep sheeted Failure | Center line shifting at hill side (Temporary) (Quantity details in SW files) Alternative alignment (Permenant) | South Rukum | Tribini RMP | 6 | Jhulneta |  | Private land, deep seated failure, |  | Private land
6 | 109050 | Type 2 | Road edge settled | GW Retaining wall, L=45m ,H=4m, Road edge damaged and crack, Pavement rehab (L=45m) | South Rukum | Tribini RMP | 6 |  |  | Road edge damages, Pipe culvert damaged | Pipe culvert, | Private land
7 | 113000 | Type 2 | Colluvim depost (Debris flow) | GW Breast wall, L=25m, H=2m, Road side drain, L=25m, Slope trimming & Bio-engineering (L=25m, H=7m) | South Rukum | Tribini RMP | 6 | Khara |  | Settlement area, Health post at the top of slide, | Crash barrier | Private land
8 | 114800 | Type 2 | Road edge damaged | GW Retaining wall, L=30m, H=4m, Road edge damaged, Pavement rehab (L=85m), Drain cum wall, L=3m, H=2m, GW Check dam, L=20m, H=3m | South Rukum | Tribini RMP | 6 | Kaprapani |  | Vegetation clearance |  | Private land
9 | 115200 | Type 3 | Surface scrap/Gully erosion | Plum Breast wall, L=45m, H=2m (upto pc) and drain cum wall, L=30m, H=2m | South Rukum | Tribini RMP | 6 | Kaprapani |  | Near settlement area, masonry wall damaged |  | Private land
10 | 116000 | Type 3 | Debris deposit | Debris clearance (L=30mx3m) and (L=25mx3m) | South Rukum | Tribini RMP | 6 | Vingring |  | Debris deposited on road, electric line passes over slide |  | Private land
11 | 120500 | Type 2 | Debris deposit | GW breast wall, L=20m, H=2m, Road side drain, L=20m, Slope trimming & Bio-engineering (L=20m, H=5m) | South Rukum | Tribini RMP | 2 | Simritu |  | Debris deposited on road, electric line passes over slide |  | Private land
12 | 123225 | Type 2 | Debris deposit from rural access Road | Pavement damaged due to Up side rural road construction, Pavement Rehab, L=300m | South Rukum | Musikot MP | 12 | Pritibang |  | Debris flow due to local road constuction, pavement damage, near settlement, irrgation canal and cultivable land valley side |  | Private land
13 | 124700 | Type 2 | Debris deposit | Pipe Culvert, Dia. 120cm, GW Check dams, L=10m, H=2m at 2 locations at up side, Debis clearance (L=10m, H=3m) | South Rukum | Musikot MP | 13 | Bairagi Thati |  | Community forest (hill side), Private land (valley side) |  | Private land
14 | 124800 | Type 2 | Debris deposit | Road side drain, L=200m, Debis clearance (L=25m, H=5m) | South Rukum | Musikot MP | 13 | Bairagi Thati |  | Community forest (hill side), Private land (valley side) |  | Private land
15 | 125200 | Type 3 | Road edge damaged | Plum retaining wall, L=15m, H=6m | South Rukum | Musikot MP |  | near solabang Bazar |  | Near solabang bazar, pipe culvert chocked and rain water flow over road and washway valley side 3 cultivated land plots |  | Private land
16 | 126550 | Type 2 | Debris deposit | Drain cum wall (2 locations), L=20m, H=1m and L=10m, H=1m , Debris clearance (3 locations), L=20m, H=3m, L=10m, H=3m & L=5m, H=3m) | South Rukum | Musikot MP | 4 | Solabang |  | Debris clearance, drain repaired, Vegetation clearance, Dust nuisence |  | Private land
17 | 127400 | Type 3 | Debris flow and deposit | Gabion Breast wall, L=45m (25+20), H=3m, Debis clearance (2 locations), L=25m, H=5m & L=20m, H=5m | South Rukum | Musikot MP | 4 | Solabang |  | Debris clearance, valleyside private land, Vegetation | Gabion breast wall | Private land
18 | 127650 | Type 3 | Road edge damaged | Gabion retaining wall, L=45m, H=8m, Pavement rehab | South Rukum | Musikot MP | 4 | Solabang |  | Near settlement area, road edge damaged and retaining wall collaps |  | Private land. Settlement Road

## S-T Road
S. N. | Landslide |  |  | Location |  |  |  | Consult With | Slide Description | Impacts |  | Environmental Mitigation Measues | Photo
| Chainage | Types of failure | Proposed Engineering Mitigation Measures | District | MP/RMP | Ward | Village |  |  | Structure | Private land
1 | 2760 | Slide at cut slope | Drain cum wall=25m, H=1.5m, Debris Clearance & Bio-engineering | Baitadi | Dasarath MP | 1 | Mushachaur | Mr. Devdatta Bhatta | Near settlement, vegatation covered land |  | Private land
2 | 2800 | Slide at cut slope | Drain cum wall=30m, H=2.0m, Debris Clearance & Bio-engineering | Baitadi | Dasarath MP | 1 | Dehimandu | Mr. Devdatta Bhatta | Near settlement, vegatation covered land |  | Private land
3 | 8750 | Gully formation | GW Check dam, L=5m, H=2m | Baitadi | Dasarath MP | 2 | Ghagharu |  | Private forest land, vegetation covered, gulley formed | Cross and side drainage, | Private land(Krishna Bohara)
4 | 29150 | Cut slope slip | Plum Breast wall extended by 10.0m, h=2.0m, Bio-engineering, Drain=10m and Slope trimming | Baitadi | Dasarath MP | 10 | Barahakot |  | Hill side private land and valley side community forest | Manonry wall | Hill side private land
5 | 29210 | Cut slope slip | Drain cum wall L=20m, H=2.0m, Slope trimming & Bio-engineering | Baitadi | Dasarath MP | 10 | Barahakot |  | Toe cut failure, | Masonry drain | Private Land

## S-G-D Road
S. N. | Landslide |  |  | Location |  |  |  | Consult With | Slide Description | Impacts |  | Environmental Mitigation Measues | Photo
| Chainage | Types of failure | Proposed Engineering Mitigation Measures | District | MP/RMP | Ward | Village |  |  | Structure | Private land
1 | 6580 | Debris slide above cut slope | Minor debris clearance, Pavement Rehb & Drain Repair |  | Surnaya RMP | 2 | Salyarde | Mr. Krishna Ram Mul (Length Worker) | Gully formation, grvaed mixed soil, previously used as quarry site |  | private land(Prakash Bhatta)
2 | 42620 | Valley side sliding due to rural road | GW Retaining wall, L=17m, H=4m, Pavement Rehab, at rural road 15m GW height 2m. |  | Dogoda Kedar RMP | 5 | Salsena | Karki | Side on valley side, road edge damaged and local acces road on valley side |  | Private land(Ser singh karki and shiva singh karki)
3 | 42750 | G/W failure due to rural road | GW, L= 25m, H=4m high at road edge and GW, L=25m, H=2m high at rural road as toe wall. |  | Dogoda Kedar RMP | 5 | Salsena |  | Side on valley side, road edge damaged and local acces road on valley side |  | Private land(Damokarki,sher Bdr karkiandRadhakarki)
4 | 46400 | G/W retaining wall failure | Gabion wall 30m length, height 6m plus plain concrete at footing with dowels 25mm dia 4m long at foundoantion block. |  |  |  | Panju Nawa |  | Valley side: Settlement below slide, Existing gabion wall collaps, Hill side: Bushes | Gabion wall | Private land(krishnakarki)
5 | 49900 | Debris flow & deposit, Gully formation | As per previous design, delete diversion structure at northern channel, Width of causeway can be reduced to 30m, guide walls to be properly embedded to rock outcrops at either end. |  | Bilasaini RMP | 6 | Bangabagar |  | Huge debris slide from hill side, road totally damaged, near settlement, the debris deposited land was previously private land |  | Private(Diwan Saud,Mahesh Raj karki,Nar Bdr saud,Dhannam saud,Dhan singh sarki,Bal Bdr saud,Ammar Nath,Jaya singh Saud)
6 | 50400 | Gabion wall failure | Minor GW repair required, length 10m height 2m, debris clearance, drain and pavement repair |  | Bilasaini RMP | 6 | Bangabagar |  | Hill side: Debris flow form rural road construction, debris deposited on road, valley side: Chaulani khola | Drain, Gabion wall, crash barrier | Private land(Kala Nath)
7 | 72820 | Cut slope failure | Gabion Breast Wall, L=27m, H=3m |  | Saileshikhar MP | 6 | Guani |  | Near water source, Hill and valley side private land with vegetation |  | Private land(kamal Singh Dhami)
8 | 73480 | Cut slope failure | Gabion Breast Wall, L=20m, H=4m |  | Saileshikhar MP | 6 | Gwani |  | Settlement area, private house near settlement, Private land, Natural water cource protection by gabion cascade | Gabion Cascade | Private land(Nainsingh Dhami)
9 | 75600 | Cut slope failure | Masonry Revetment Wall, L=20m, H=3m |  | Saileshikhar MP | 6 | Ullayan | Mr. Kale Dhami | Settlement area, private cultivable land |  | Private(kala Dhami)
10 | 76560 | Landsldie at cut slope | Gabion Breast Wall, L=35m, H=3m, Side drain, L=35m, Bio-engg, Slope trimming, stone riprap and boulder removal |  | Saileshikhar MP | 6 | Lauri | Mr. Birendra Singh Dhami | Hill side: Private land, Valley side: Barren land, side on hill side |  | Private(Bhaskar singh dhami,keshar singh dhami and kishan dhami)
11 | 83570 | P/C failure | Pipe Culvert (existing PC washout), GW retaining wall, L=40m, H=5m |  | Malika Arjun RMP | 3 | Uttisa Patal |  | Private forest, Hill and valley side vegetation, | Gabion wall damaged | Private(Harilal Dhami)
12 | 113880 | Problem caused by debris flow event in 2072 monsson, a few houses washed away including 15m span bridge at Kakragad. New 25m span bridge under construction | Drain cum wall, L=60m, H=1.5m, GW breast wall, L=50m, H=2m, GW retaining wall, L=30m, H=5m. Depends on bridge approach constructed by the DRO. |  | Mahakali MP | 8 | Kaakada |  | Near settlement, Kakadaged khola, Near confluence point to Mahakali river | Bridge is under construction by DRO, | Private(Premsingh Mahara)

## S-J Road
S. N. | Landslide |  |  | Location |  |  |  | Consult With | Slide Description | Impacts |  | Photo
| Chainage | Types of failure | Proposed Engineering Mitigation Measures | District | MP/RMP | Ward | Village |  |  | Structure | Private land
1 | 54500 | SRF(M), EDF(M), RE/U(S), PF(S), DB(S) | Gabion Breast wall, L=100m, H=2m, Road side Drain and Sub-surface Drain of 800m, Gabion Retaining Wall, L=100m, H=4m | Dailekh | Gurash RMP | 1 | Timile khola | purna Bdr rawot | Settlement area, hill side: cultivale land, irrigation canal, Valley side: House, banana trees |  | Private land
2 | 134+450 | R fall | Large Boulders (12 nos.) falls on the Road and Gabion Breast Wall damaged, Gabion Breast Wall, L=8m, H=3m, Gabion Breast Wall, L=5m, H=2m, Road Side Drain, L=15m, Bio-engineering | Kalikot | Khadachakra MP | 2 | Sherighat | Bharat Sharma | Near water course, fracture rock piece slide along road side |  | Private land
3 | 140400 |  | Debris and Boulder clearance & Bio-engineering, L=20m, H=7.5m | Kalikot | Khadachakra MP | 2 | Sherighat | Bharat Sharma | Settlement area, local access constructed |  | Private land
4 | 140500 |  | Gabion Retaining Wall, L=10m, H=4m | Kalikot | Khadachakra MP | 2 | Sereghat | keshab B.K | Road edge damaged, and covered private land |  | Private land
5 | 144700 |  | Gabion Breast Wall, L=12m, H=3m, Road Side Drain, L=12m | Kalikot | Khadachakra MP | 2 | Kayegad | keshab B.K | Near water course, Private land |  | Private land
6 | 145810 |  | Road Side Drain & Sub-surface Drain in seepage area, L=150m, Gabion Breast Wall, L=120m, H=3m, Causeway, Span=6m (Existing Kholsi is diverted by rual access Road) | Kalikot | Khadachakra MP | 2 | Sunara Khola | keshab B.K | Private land, water flow over road, water mill in operation, |  | Private land
7 | 147400 |  | Gabion Breast Wall, L=20m, H=3m (extension from existing GW), Road Side Drain on both side of Causeway, L=50m & 30m, Check Dam at 2 locations (L=5m, H=3m), Debris clearance from Road, L=50m, width=2.5 & T=1m | Kalikot | Khadachakra MP | 2 | Sunara Khola | Kirparam Baral | Natural water course, pavement damaged, rural road L/S of channel |  | Private land
8 | 148600 |  | Gabion Breast Wall, L=30m, H=3m, Gabion Breast Wall, L=60m, H=3m, Gabion Retaining Wall (near house access), L=10m, H=3m, Gabion Retaining Wall, L=30m, H=4m, Gabion Retaining Wall, L=25m, H=5m, Road Side Drain, L=100m, Slope trimming and bio-engineering (after rocky area), L=90m, H=10m | Kalikot | Khadachakra MP | 2 | Sunara Khola | Kirparam Baral | Near settlement, debris flow over road and pavement damaged, Private structure near slide, | Private structure
9 | 151500 |  | Gabion Breast Wall, L=10m, H=2m, Road Side Drain, L=25m | Kalikot | Khadachakra MP | 1 | Sunara Khola | Kirparam Baral | Hill side barran land, valley side settlement |  | Private land
10 | 155390 | SRF(R), PF(S), DB(S) | Plum Concrete Breast Wall, L=20m, H=3m, Road Side Drain, L=50m, Causeway, Span=4m at valley, Bio-engineering, L=30m, H=15m | Kalikot | Khadachakra MP | 3 | Tadi | Kirparam Baral | Private land around 200 m from manma bazar, debris flow over road |  | Private land
11 | 161480 |  | Gabion Breast Wall, L=15m, H=2m (Existing GW is damaged), Road Side Drain, L=15m, Slope Trimming and Bio-engineering (L=15m+10m and H=5m), Debris Clearance, L=15m, H=5m, Gabion Breast Wall, L=20m, H=2m, Road Side Drain, L=20m | Kalikot | Khadachakra MP | 5 | Maulaghari | nanda shahi | Hill side barran land, | Gabion breast wall | Private land
12 | 166300 |  | Gabion Breast Wall, L=30m, H=3m, Road Side Drain, L=30m, Bio-engineering, L=30m, H=7m | Kalikot | Khadachakra MP | 5 | Paira Khola | nanda shahi | Surface erosion by rain water, cultivable land at foothill | Gabion breast wall, Masonry retaining wall | Private land
13 | 169490 |  | Road Side Drain, L=75m, Boulder Clearance | Kalikot | Khadachakra MP | 6 |  | nanda shahi | Rock slide into land, Drain covered by debris, barren land, rock being used by local | Gabion breast wall | Private land
14 | 173770 |  | Gabion Breast Wall, L=20m, H=3m, Road Side Drain, L=20m, Debris Clearance, L=10m, H=10m, T=2m, Slope trimming and bio-engineering (L=10m, H=10m) | Kalikot | Khadachakra MP | 7 | Pili | Danta malla | Mud slide, water pipe passes through slide location, | drinling water pipeline | Private land
15 | 174110 |  | Plum Concrete Breast Wall, L=20m, H=3m (before access Road), Gabion Breast Wall, L=30m, H=3m, Drain, L=50m, Debris clearance from Road and hill slope | Kalikot | Khadachakra MP | 7 | Pili | Danta malla | Slide due to local road construction, house is in threats nearby | Structures
16 | 174200 |  | Gabion Breast Wall, L=15m, H=2m, Drain, L=15m, Boulder and Debris Clearance, L=15m, H=5m | Kalikot | Khadachakra MP | 7 | Pili | Danta malla | Near settlement, rock slide into road | settlement
17 | 191210 |  | Gabion Breast Wall, L=7m, H=2m (extension from existing), Road Side Drain, L=7m, Boulder Clearance | Kalikot | Tila Gufa MP | 6 | Galje | Danta malla | Tila river valley side, debris and boulder slide |  | Private land